## Slide 1: Status of Mercury Project
Report to TEC Committee
June 6-7, 2017

## Slide 2: Committee Charge
  Identify what is known and unknown about mercury.
  Determine the value and costs of addressing the unknowns.
  Make recommendations for studies to the Commission.

## Slide 3: Committee Background
  Ad Hoc Established June, 2015.
  Held 5 conference calls.
  1 in-person meeting at ORSANCO Aug. 3.

## Slide 4: Committee Background (cont.)
  Identified available outside data.
  Completed comprehensive literature review.
  Completed background report based on lit. review.
  Identified and prioritized information needs.
  Identified a project and schedule to fill in information gaps.

## Slide 5: Committee Membership
Stuart Bruny OH Commissioner
George Elmaraghy Federal Commissioner
Erich Emery US Army Corps of Engineers
Tom FitzGerald Federal Commissioner
Madeline Fleisher Environmental Law & Policy Center
Toby Frevert IL Commissioner
Tim Henry USEPA
John Kupke (Chair) IN Commissioner
Paul Novak IDEM/TEC NPDES Chair
Eric Nygaard OEPA
Ron Potesta WV Commissioner
Rob Reash Power Industry Advisory Committee
Martin Risch USGS
Mike Wilson NY Commissioner
Doug Conroe NY Commissioner
Jessica Dexter ELPC
Eileen Hack IDEM
Ron Lovan Commission Chairman (Kentucky)

## Slide 6: Identified Information Needs
Priority #1:
  Mass Balance to quantify and apportion sources of mercury in Ohio River.
  Are point sources are having an impact and what is the magnitude of the impact?
  These questions would lead towards development of appropriate management scenarios.

## Slide 7: Aspects of the Mercury Mass Balance Study
Considered various approaches.
Decided on a point source focus.
Relies heavily on existing studies and information.
Very low cost project. Completed with existing staff. No special studies/surveys/projects needed to complete the effort.

## Slide 8: Mass Balance/Source Apportionment
1) Calculate mass loads in Ohio River.
    Based on existing mainstem studies.
    Bottom of each pool where data allows.
2) Calculate mass loads from 15 largest tribs.
    Accounts for approx. 85% of watershed.
    Includes ~85% of atmospheric deposition.
    Based on current sampling effort.

## Slide 9: Tributary Loads

## Slide 10: Mass Balance/Source Apportionment (cont.)
3) Calc. mass loads for Ohio River point sources.
    Use existing data in data bases.
    Extrapolate where appropriate based on SIC codes.
Calc. mass loads for trib point sources.
5) Estimate atmospheric deposition on sub- watershed basis.
6) Putting It All Together.
    Estimate percent contribution from all sources.

## Slide 11: What is Known About Ohio River Point Sources
569 permitted discharges (not general permits).
26 have Hg effluent limits; 88 monitoring reqs.
177 WWTPs; 10 have limits; 44 have DMR data.
Will extrapolate to the WWTPs without data.

## Slide 13: Project Timeline