## Slide 1
Information Item

## Slide 2
Bacteria TMDL for entire length of Ohio River
TMDL effort led by US EPA Region 5
  Tetra Tech lead contractor
ORSANCO Role
  Ambient monitoring data collection (Ohio R and tribs)
  TMDL workgroup routinely meets by conference call to discuss progress

## Slide 3
Data Collection
  EPA received additional data from KY DOW and several municipalities to better define CSO loadings
  Still need data from several CSO communities
  Request made to POTW Committee for additional data (November 1 deadline)
Modeling
  Working with US Army Corps of Engineers to add WQ module to HEC-RAS model
  Continue to build boundary conditions

## Slide 4
Calibration to begin in November once new data are incorporated into model.
Need to define allocation strategy
  States can provide input upfront or in response to draft allocation strategy once developed

## Slide 5
Timeline provided by EPA
Tasks 1-6 will be ~2 months behind schedule due to CSO data request deadline of Nov 1
Task 1 | Refine, Calibrate/Validate model | 10/18/13
Task 2 | Complete Modeling Results Report | 12/19/13
Task 3 | TMDL Scenario Modeling Efforts | 02/01/14
Task 4 | Development of Draft TMDL | 02/28/14
Task 5 | TMDL Workgroup Meeting | 03/03/14
Task 6 | Public Meetings | 03/19/14
Task 7 | Development of Final TMDL | 09/30/14